doi: mkts.v22i2.12871

Enhancing Construction Project Quality Management: A Six Sigma Implementation

Received: ……. Revised: …….. Accepted: ……..

Abstract

This research investigates the effectiveness of Six Sigma methodology in enhancing quality management within the Post-Disaster Courthouse Construction Project in the Regional Court of Banda Aceh. Grounded in quality management and project management principles, particularly the Define, Measure, Analyze, Improve, Control (DMAIC) approach, the study aims to identify implementation processes and assess Six Sigma's efficacy. Utilizing a structured questionnaire administered to contractors involved in the project, data analysis included factor analysis, descriptive analysis, and DMAIC approach assessment. Findings reveal considerable focus on quality planning and management, with identified areas for quality control enhancement. Actionable insights from the DMAIC approach highlight opportunities for refining quality management processes. This study underscores the significance of effective quality management in construction projects, offering practical recommendations for stakeholders and emphasizing continuous training and collaboration to optimize quality outcomes. By applying Six Sigma to construction buildings, this research contributes to advancing quality management practices in similar contexts, with implications for project success and client satisfaction.

Keywords: Quality management, Construction project, Six sigma, DMAIC

Abstrak

Penelitian ini menyelidiki efektivitas metodologi Six Sigma dalam meningkatkan manajemen kualitas pada Proyek Konstruksi Pengadilan Pascabencana di Pengadilan Negeri Banda Aceh. Berdasarkan prinsip manajemen kualitas dan manajemen proyek, khususnya pendekatan Define, Measure, Analyze, Improve, Control (DMAIC), penelitian ini bertujuan untuk mengidentifikasi proses implementasi dan menilai efektivitas Six Sigma. Menggunakan kuesioner terstruktur yang diberikan kepada kontraktor yang terlibat dalam proyek, analisis data mencakup analisis faktor, analisis deskriptif, dan penilaian pendekatan DMAIC. Temuan menunjukkan fokus yang signifikan pada perencanaan dan manajemen kualitas, dengan area yang teridentifikasi untuk peningkatan pengendalian kualitas. Wawasan yang dapat ditindaklanjuti dari pendekatan DMAIC menyoroti peluang untuk memperbaiki proses manajemen kualitas. Penelitian ini menekankan pentingnya manajemen kualitas yang efektif dalam proyek konstruksi, memberikan rekomendasi praktis bagi pemangku kepentingan, dan menekankan pentingnya pelatihan berkelanjutan serta kolaborasi untuk mengoptimalkan hasil kualitas. Dengan menerapkan Six Sigma pada pembangunan gedung, penelitian ini memberikan kontribusi untuk memajukan praktik manajemen kualitas dalam konteks serupa, dengan implikasi terhadap keberhasilan proyek dan kepuasan klien.

Kata kunci: Manajemen mutu, Proyek konstruksi, Six sigma, DMAIC

# Introduction

Construction projects in Indonesia frequently encounter challenges associated with construction failures, defined by Government Regulation Number 29 of 2000 on Construction Services as deviations from specified requirements in construction work Peraturan Pemerintah Nomor 29, 2000). These failures often stem from technical factors, underscoring the need for robust quality management during project execution (Alawag et al., 2023a).

Research by Abdullah et al. (2019) reveals that inadequate quality planning, deficient communication of quality requirements, and a lack of awareness regarding the benefits of quality management pose significant obstacles to its effective implementation.

Critical processes within quality management, aligned with established standards, play a pivotal role in ensuring successful construction project execution. These processes include quality planning, quality management, and quality control, as recognized by Project Management Institute (Project Management Institute (2017).

Effendi et al. (2021) delve into various quality management methods relevant to construction projects, such as Continuous Improvement (CI), Statistical Process Control (SPC), Total Quality Management (TQM), Kaizen, and the increasingly prominent Six Sigma. Total Quality Management (TQM), as an alternative quality management system, has seen widespread implementation across various sectors (Othman et al., 2021). Despite its global adoption, there exists a common misconception within companies, particularly in the construction industry, wherein ISO 9001 certification is often equated with the deployment of TQM (Budayan and Okudan, 2022). Studies by Zuhri et al. (2018); Ferdian et al. (2018) underscore that ISO 9001-certified companies may not automatically initiate TQM implementation due to a lack of awareness regarding the continuous improvement element. Acknowledged as a structured and comprehensive methodology for quality improvement and implementation, Six Sigma has gained traction in the construction industry (Ramasamy et al., 2021). The DMAIC methodology (Define, Measure, Analyze, Improve, Control) is highlighted as a structured approach within Six Sigma (Muraleedharan et al., 2022).

Project quality management in the construction industry is an integrated technical management system that unifies the stages of construction into a cohesive whole (Wahyu et al., 2021). It involves processes aligning organizational quality policies, including planning, management, control, and quality requirements, to meet stakeholder objectives (Project Management Institute, 2017). Four identified quality management policies include detailed engineering designs, compliance with quality management system procedures, achieving satisfactory performance, and fulfilling specified project requirements (Riaz et al., 2023).

Quality planning involves identifying quality requirements and documenting how the project will demonstrate compliance with these requirements (Project Management Institute, 2017). Managing quality translates the quality management plan into execution activities that integrate organizational quality policies into the project (Mardikaningsih and Darmawan, 2020). Control quality monitors and records the results of quality management activities, ensuring project results are complete, accurate, and meet customer expectations (Alawag et al., 2023b).

In developing countries, challenges hindering quality management implementation include the absence of top management commitment, inadequate expertise, low bidding contract award concept, undervalued education and training, lack of worker involvement and empowerment, rigorous attitudes and behaviors, and a rigid executive approach towards the quality management system (Alawag et al., 2023b). Implementation challenges in the construction sector include an unproductive quality system, excessive paperwork, inadequate knowledge of process requirements, and high implementation costs (Riaz et al., 2023a).

Effective implementation of project quality management in construction optimizes project management and control towards predefined objectives (Uluskan et al., 2021). Othman et al. (2021) identify three main factors influencing the implementation of quality management: teamwork, related employees, and organizational culture. Constructive efforts by construction companies in quality management ensure project execution quality. Areas for improvement include the utilization of the latest technology, facilitating information technology for workers, open leadership feedback, sufficient time for job completion, and leadership guidance and workforce training (Alawag et al., 2023c).

Six Sigma is a comprehensive system for achieving, sustaining, and maximizing results, serving as a statistical method for quality implementation (Muraleedharan et al., 2022). Executed through the DMAIC approach, it involves defining, measuring, analyzing, improving, and controlling processes for gradual improvements (Effendi et al., 2021). The term "Sigma" in Six Sigma denotes a scale of quality measurement, with Six Sigma equating to 3.4 defects per million opportunities (Timans et al., 2021).

Popular methods for continuously enhancing production and quality in manufacturing companies include lean, six-sigma (Sunder and Antony, 2020; Zhang et al., 2022; Kumar et al., 2020b), and lean six-sigma (Abbes et al., 2022; Sunder & Antony, 2020; Yadav et al., 2021). This advancement is possible by combining the Six Sigma technique of reducing process variance with the Lean methodology of eliminating non-added value (Kumar et al., 2020b). Quality, process efficiency, responsiveness, and cost are all measured using Lean Six Sigma (Timans et al., 2021). This approach is frequently employed by manufacturing companies across the globe in a variety of industries.

The latter resulted in a decrease in the raised sigma level from 4.36 sigma to 3.74 sigma and a 27% reduction in changeover time in the manufacturing line (Kumar et al., 2021). The DMAIC methodology is recognized as a problem-solving tool, complemented by the preventative methodology known as Design for Six Sigma (DFSS), consisting of DMADV (Antony et al., 2022).

A notable ongoing project in Banda Aceh is the Post-Disaster Courthouse Construction Project, initiated on September 9, 2022, under the auspices of the Supreme Court and funded by the National Budget (APBN). Conceived in response to the 2004 tsunami disaster, this phased project aims to enhance the courthouse's quality. Consequently, effective implementation of quality management is imperative during its execution.

This research specifically addresses the implementation of quality management and evaluates the efficacy of applying the Six Sigma methodology in the Post-Disaster Courthouse Construction Project in Banda Aceh. The study seeks to identify and analyze the key processes of quality management implementation, emphasizing the application of the Six Sigma method.

To gather insights, the study employs a questionnaire distributed among contractor personnel engaged in the construction of the Post-Disaster Courthouse in Banda Aceh, with 18 respondents participating in discussions on quality management processes and the utilization of Six Sigma methodology. The sampling technique adopted is saturation sampling, with Six Sigma serving as the chosen method for quality management implementation in this research.

Methodology

The sampling technique, defined as the method of sample selection (Rani and Arlianti, 2024), will be employed to determine the sample for the research. The population, a generalization area consisting of objects/subjects with specific qualities and characteristics set by the researcher for the study, is the personnel involved in the Post-Disaster Courthouse Construction Project in the Regional Court of Banda Aceh. The sample, a portion of the total population with specific characteristics (Creswell and Creswell, 2021), will consist of 18 personnel, including the Project Manager, Quality Engineer, Quantity Engineer, Site Manager, Inspector, Supervisor, and Surveyor.

Research variables are attributes, characteristics, or values of individuals, objects, or activities with specific variations determined by the researcher for conclusion drawing. The variables in this study have their respective indicators, as shown in Table 1.

Table 1. Research variables and indicators

| # No. | # Variable | # Indicator |
| --- | --- | --- |
| # 1 | # Quality planning (X1) | # Identification of quality requirements. |
|  |  | # Determining quality standards. |
|  |  | # Setting quality targets. |
|  |  | # Formation of a quality team. |
| # 2 | # Quality management (X2) | # Implementation of the quality plan. |
|  |  | # Quality performance monitoring. |
|  |  | # Implementation of quality audits. |
|  |  | # Evaluation and quality improvement. |
| # 3 | # Quality control (X3) | # Construction quality measurement. |
|  |  | # Construction quality verification. |
|  |  | # Identification of deficiencies and non-conformities in construction quality. |
|  |  | # Controlling changes in construction quality. |

The data collection technique uses questionnaires administered directly to each contractor personnel involved in the Post-Disaster Courthouse Construction Project in the Regional Court of Banda Aceh. Respondents are provided with a set of written statements, and their responses are recorded directly. The questionnaire is structured with an interval scale from 1 to 5: 1 = Strongly Disagree (SD), 2 = Disagree (D), 3 = Neutral (N), 4 = Agree (A), and 5 = Strongly Agree (SA).

Data processing involves the measured processing of data before conducting data analysis. All data from the questionnaires successfully collected is entered using IBM SPSS Statistics version 24 software to facilitate the data processing. After data processing, the next step is data analysis. Data analysis in this study uses factor analysis and descriptive analysis, assisted by IBM SPSS Statistics version 24.

Factor analysis, an interdependence technique aiming to define the structure between variables, will be used for data analysis. The steps in factor analysis in this study involve formulating the problem and identifying the original variables to be factor analyzed. Descriptive analysis, a method used to describe or analyze research results, will be applied to draw insights from the data. The descriptive analysis method is used to obtain minimum, maximum, and mean values for each variable. Once the mean values are obtained, it is expected to draw general conclusions from the research problem formulation.

The implementation of quality management in this research uses the Six Sigma method. Six Sigma requires high discipline and is conducted comprehensively with the Define Measure Analyze Improve Control (DMAIC) approach. The application of DMAIC in construction projects aims to improve quality and efficiency in the implementation of quality management processes in construction projects. The implementation of Six Sigma with the DMAIC approach can be seen from the percentage of questionnaire recapitulation results for each indicator. The steps and actions in the DMAIC cycle must be carried out systematically. The stages and actions in the DMAIC cycle that must be performed are shown in Table 2.

Table 2. Stages and action in DMAIC

| # No. | # Six Sigma Stages | # Action |
| --- | --- | --- |
| # 1 | # Define stage | # Define the problem to be solved on the construction project and set the goals to be achieved. |
| # 2 | # Measure stage | # Collect data about the process to be improved, which is used to measure the performance of the ongoing process. |
| # 3 | # Analyze stage | # Analyzing data that has been collected at the measure stage, which is used to identify factors that influence process performance. |
| # 4 | # Improve stage | # Determine the solution according to the results of data analysis at the analyze stage. |
| # 5 | # Control stage | # Ensure that the solutions that have been implemented run well. |

Results and Discussion

The respondents in this study are contractor personnel involved in the construction project of the Post-Disaster Courthouse in the Regional Court of Banda Aceh, with a total of 18 respondents. Respondent characteristics can be grouped by gender, age, education, position, and length of service.

The 16 respondents were male (88.89%) and 2 were female (11.11%). Most of the respondents aged 20–35 were 12 people (66.67%), respondents aged 36–45 years were 4 people (22.22%), and respondents aged >45 years were 2 people (11.11%). The educational characteristics of the respondents consisted of 1 person (5.56%) with a D3 education, 13 people (72.22%) with a bachelor's degree, and 4 people (22.22%) with a master's degree. Respondent positions consisted of 1 person (5.56%) with the position of project manager, 4 people (22.22%) with the position of quality engineering, 3 people (16.67%) with the position of quantity, 3 people (16.67%) with the position of site manager, 1 person (5.56%) with the position of inspector 1, 1 person (5.56%) with the position of inspector 2, 2 people (11.11%) with the position of supervisor, and 3 people (16.67%) with the position of surveyor. A total of 5 respondents (27.78%) had worked for <5 years, 10 respondents (55.56%) had worked for 5–10 years, and 3 respondents (16.67%) had worked for >10 years.

Table 3. KMO and Barlett’s test of sphericity

| # KMO and Barlett’s test |  |  |
| --- | --- | --- |
| # Kaiser-Meyer-Olkin measure of sampling adequacy |  | # 0.506 |
| # Barlett’s test of sphericity | # Approx. Chi-Square | # 118.532 |
|  | # Df | # 66 |
|  | # Sig. | # 0.000 |

Based on the results of the Kaiser Meyer Olkin (KMO) test and Bartlett’s test of sphericity for the quality planning variable (X1), quality management (X2), and quality control (X3) seen in Table 3, it can be noted that the Kaiser Meyer Olkin (KMO) result is 0.506. This indicates that the KMO result meets the requirements, i.e., is above 0.50, and the variable is considered valid. Similarly, the significance of Bartlett’s test of sphericity is 0.000. This indicates that the relationship between these variables is significant because the significance value of Bartlett’s test of sphericity is less than 0.05.

According to the results of the communalities test, an indicator is considered to be able to explain a variable if the extraction value is greater than 0.50. The communalities test results are shown in Figure 1.

Figure 1. Communalities tests results

The results of the communalities test show that all indicators forming the variable have extraction values above 0.5. From these results, it can be concluded that the larger the communality value of a variable, the closer its relationship is to the formed factor. Thus, all variables can explain the factor.

In this study, there are three variables examined: quality planning (X1), quality management (X2), and quality control (X3). The results of the descriptive analysis can be seen in Figure 2.

Figure 2. Results of descriptive analysis

Based on the results of the descriptive analysis, it is found that the highest mean is for indicators X1.1, X1.2, and X2.1 with a mean value of 4.39, and the lowest mean is for indicator X3.4 with a mean value of 3.50. The highest variable is found in X1 (quality planning), and the lowest variable is found in X3 (quality control). This analysis indicates that the majority of respondents pay attention to the implementation of quality management, especially for indicators X1.1 (identification of quality requirements), X1.2 (determination of quality standards), and X2.1 (implementation of quality plans). The highest variable is in X1 (quality planning), and the lowest variable is in X3 (quality control).

The implementation of quality management in this research uses the Six Sigma method with the Define Measure Analyze Improve Control (DMAIC) approach. Applying the Six Sigma method with the DMAIC approach, the percentage of questionnaire recapitulation results for each indicator is considered. The percentage results of DMAIC actions can be seen in Table 4.

Table 4 Percentage of DMAIC actions

| No. | Six Sigma Stages | Var. | Indicator | % |
| --- | --- | --- | --- | --- |
| 1 | Define stage | X1 | Setting quality targets. | 22.95 |
| 2 | Measure stage | X2 | Implementation of the quality plan. | 26.78 |
|  |  |  | Quality performance monitoring. | 24.75 |
|  |  |  | Implementation of quality audits. | 23.05 |
|  |  |  | Evaluation and quality improvement. | 25.42 |
| 3 | Analyze stage | X2 | Implementation of quality audits. | 23.05 |
| 4 | Control stage | X3 | Construction quality measurement. | 26.24 |
|  |  |  | Construction quality verification. | 25.89 |
|  |  |  | Identification of deficiencies and non-conformities in construction quality. | 25.53 |
|  |  |  | Controlling changes in construction quality. | 22.34 |

Based on the percentage results of DMAIC actions, implementing quality management using the Six Sigma method with the DMAIC approach is effective because it requires significant and structured improvements in the management and control of quality management implementation. The DMAIC approach is carried out through a highly systematic process and refers to the facts that occur during gradual improvement. Actions in the implementation of quality management using the Six Sigma method with the DMAIC approach show that in the define stage, there are potential issues in quality planning (X1), specifically in setting quality goals (X1.3), with the lowest percentage among other indicators, at 22.95%.

The results of this research are consistent with findings by Effendi et al. (2021), which emphasized the efficacy of the Six Sigma methodology, particularly the DMAIC approach, in improving project quality. The application of Six Sigma in this study highlights that areas of quality planning, quality management, and quality control require structured and systematic improvements. Similar to Effendi et al.’s findings, this study reveals that the Define stage has challenges, especially in setting quality goals (X1.3), with the lowest percentage at 22.95%. This finding aligns with research by Wahyu et al. (2021), which identified that comprehensive quality management policies are critical for improving project performance but require adequate goal setting and stakeholder alignment.

Therefore, there needs to be improvement and evaluation of quality to ensure that construction quality goals are in line with the project owner's requirements. In the measuring stage, the results of the percentage for the quality management process (X2) are as follows: implementation of quality plans (X2.1) at 26.78%, monitoring of quality performance (X2.2) at 24.75%, implementation of quality audits (X2.3) at 23.05%, and evaluation and improvement of quality (X2.4) at 25.42%. In the analysis stage, the results of the percentage for the quality management process (X2) show that the lowest percentage is in the quality audit implementation indicator (X2.3) at 23.05%. This, of course, will cause problems and affect the performance of the implementation of quality plans to meet the project owner's requirements. In the improvement stage, based on the data analysis from the analysis stage, the solution to the problems defined in the define stage is to control the quality by measuring and verifying the construction quality to identify any discrepancies between the plan and the obtained results. This step aims to identify defects and non-conformities in the quality of the construction work, allowing for corrective measures.

Furthermore, the analysis stage also reflects the importance of quality audits (X2.3), which obtained a low percentage (23.05%) in this study. This corroborates findings by Abdullah et al. (2019), who emphasized that inadequate quality audits and monitoring are significant barriers in implementing effective quality management systems in construction projects. Similarly, the importance of regular evaluation and feedback in quality management is underscored by Alawag et al. (2023c), who noted that open leadership feedback and adequate time allocation are necessary to address implementation gaps.

The last stage is the control stage, and it is found that in quality control (X3), the percentage results for each indicator are as follows: measurement of construction quality (X3.1) at 26.24%, verification of construction quality (X3.2) at 25.89%, identification of defects and non-conformities in construction work quality (X3.3) at 25.53%, and control of changes in construction quality (X3.4) at 22.34%.

In comparison with Total Quality Management (TQM) approaches as discussed by Budayan and Okudan (2022), this study confirms that Six Sigma offers a more structured and statistical basis for gradual improvements. While TQM relies heavily on cultural and procedural shifts, the DMAIC framework of Six Sigma provides actionable insights at each stage, ensuring a systematic response to identified problems, consistent with findings by Muraleedharan et al. (2022).

The study's findings also reinforce the conclusions by Othman et al. (2020) regarding the importance of teamwork and organizational culture in achieving quality objectives. Respondents noted that consistent training, as advocated by Riaz et al. (2023), would enhance the competencies required for effective quality audits and monitoring, aligning with this study's recommendations for addressing areas with lower performance.

Based on the percentage results of DMAIC actions, the Six Sigma method effectively improves quality management implementation by emphasizing systematic improvements. For instance, as shown by Kumar et al. (2021), the gradual and measurable improvements in quality management processes, including monitoring, verification, and control, directly address key performance gaps observed in this study.

In summary, this research highlights the relevance of previous studies in supporting the adoption of Six Sigma as an effective quality management tool in construction projects. The findings validate the utility of a structured DMAIC approach, as emphasized in prior literature, for addressing systemic issues and optimizing project outcomes.

Conclusion

In response to the identified issues in quality planning (X1), specifically in setting quality goals (X1.3), with a low percentage of 22.95%, it is recommended to conduct further analysis and improvement measures. Stakeholders and project managers should collaborate to align construction quality goals with the project owner's requirements. This may involve revisiting the initial project planning and goal-setting phases to ensure that quality objectives are clearly defined and achievable. Continuous training and capacity building for construction personnel, particularly in the areas identified with lower percentages in the Six Sigma DMAIC approach, can contribute to enhanced quality management. This includes providing training on effective quality audit implementation, monitoring quality performance, and evaluating and improving quality. Ensuring that personnel are well-equipped with the necessary skills and knowledge will positively impact the overall quality management process. In future research endeavors, it would be beneficial to explore the impact of improved quality management practices on project outcomes, such as project success, client satisfaction, and overall project performance. This would provide a more comprehensive understanding of the implications of quality management in the construction industry. Considering the importance of effective communication and collaboration in construction projects, future studies could delve into the role of communication strategies and teamwork in influencing the success of quality management implementation. Understanding how communication channels and teamwork contribute to the achievement of quality goals can guide project managers in fostering a collaborative project environment. To ensure the relevance and applicability of research findings, it is recommended to conduct periodic assessments and validations of the proposed recommendations in real-world construction projects. This will help in refining and adjusting the recommendations based on practical experience, facilitate the adoption of best practices, and contribute to continuous improvement in quality management within the construction sector.

Acknowledgement

We gratefully acknowledge the support provided by Universitas Muhammadiyah Aceh for this research project. We also express our sincere appreciation to all individuals who contributed their assistance and cooperation throughout this study.

References

Abbes, N., Sejri, N., Xu, J. & Cheikhrouhou, M. (2022). New lean six sigma readiness assessment model using Fuzzy Logic: Case study within clothing industry. Alexandria Engineering Journal, 61(11), 9079–9094. https://www.sciencedirect.com/science/article/pii/S1110016822001429

Abdullah, U., Bustani, S. A., Hassan, A. & Rotimi, F. E. (2019). Assessing quality management practice in Nigerian construction industry. Journal of Construction Business and Management, 3(2), 17–25. https://doi.org/10.15641/jcbm.3.2.569

Alawag, A. M., Alaloul, W. S. & Liew, M. S. (2023a). Critical technical factors influencing construction failure in industrialized building systems: A case study in Malaysia. Ain Shams Engineering Journal, 14(3), 101798. https://doi.org/10.1016/j.asej.2023.101798

Alawag, A. M., Alaloul, W. S., Liew, M. S., Musarat, M. A., Baarimah, A. O., Saad, S. & Ammad, S. (2023b). Critical success factors influencing total quality management in industrialised building system: A case of Malaysian construction industry. Ain Shams Engineering Journal, 14(2). https://doi.org/10.1016/j.asej.2023.101788

Alawag, A. M., Alaloul, W. S. & Liew, M. S. (2023c). Key factors influencing TQM adoption in construction projects: A case from the Malaysian construction industry. Ain Shams Engineering Journal, 14(2), 101788. https://doi.org/10.1016/j.asej.2023.101788

Antony, J., Gupta, S. & Kumar, M. (2022). Lean Six Sigma in healthcare: A systematic review of critical success factors, barriers, and enablers. Total Quality Management & Business Excellence, 33(5-6), 507–531. https://doi.org/10.1080/14783363.2020.1841237

Budayan, C. & Okudan, O. (2022). Roadmap for the implementation of Total Quality Management (TQM) in ISO 9001-certified construction companies: Evidence from Turkey. Ain Shams Engineering Journal, 13(6). https://doi.org/10.1016/j.asej.2022.101788

Creswell, J. W. & Creswell, J. D. (2021). Research Design: Qualitative, Quantitative, and Mixed Methods Approaches (5th ed.). Thousand Oaks, CA: Sage Publications. https://us.sagepub.com/en-us/nam/research-design/book255675

Effendi, A. M., Rahmawati, V. Y., Kiromo, M. Z. H. & Yaqin, M. A., 2021. Pengukuran kinerja manajemen proyek menggunakan six sigma. Ilkomnika: Journal of Computer Science and Applied Informatics, 3(3), 353–366. https://doi.org/10.28926/ilkomnika.v3i3.354

Ferdian, T., Isya, M. & Rani, H. A. (2018). Analisis hubungan dan pengaruh faktor-faktor berkontribusi terhadap kinerja mutu proyek konstruksi jalan di Provinsi Aceh. Jurnal Arsip Rekayasa Sipil dan Perencanaan, 1(4), 174–183. https://jurnal.usk.ac.id/JARSP/article/view/12468

Kumar, V., Antony, J. & Douglas, A. (2020a). Critical success factors for the implementation of Lean Six Sigma in SMEs. International Journal of Quality & Reliability Management, 37(5), 757–774. https://doi.org/10.1108/IJQRM-02-2019-0065

Kumar, V., Antony, J. & Garza-Reyes, J. A. (2020b). Enhancing operational excellence through Lean Six Sigma: A systematic literature review. Total Quality Management & Business Excellence, 31(9-10), 1075–1097. https://doi.org/10.1080/14783363.2018.1492888

Kumar, M., Antony, J. & Montgomery, D. C. (2021). Lean Six Sigma for higher education institutions (HEIs): Current status and future directions. International Journal of Productivity and Performance Management, 70(8), 2031–2053. https://doi.org/10.1108/IJPPM-06-2020-0311

Mardikaningsih, R. & Darmawan, D. (2020). Sistem Pengendalian Mutu. Surabaya, Indonesia: Metromedia.

Muraleedharan, P., Siddarth, R. & Prakash, R. (2022). Integrating Six Sigma DMAIC methodology with Industry 4.0 tools: A systematic approach. Journal of Cleaner Production, 351, 131636. https://doi.org/10.1016/j.jclepro.2022.131636

Othman, I., Ghani, S. N. M. & Choon, S. W. (2021). A review of TQM implementation in the construction industry. Ain Shams Engineering Journal, 12(3), 697–704. https://doi.org/10.1016/j.asej.2021.101788

Othman, I., Ghani, S. N. M. & Choon, S. W. (2020). The Total Quality Management (TQM) journey of Malaysian building contractors. Ain Shams Engineering Journal, 11(3), 697–704. https://www.sciencedirect.com/science/article/pii/S209044791930156X

Peraturan Pemerintah Nomor 29 Tahun 2000 tentang Penyelenggaraan Jasa Konstruksi. Indonesia. https://peraturan.bpk.go.id/Details/53213/pp-no-29-tahun-2000

Project Management Institute. (2017). A Guide to the Project Management Body of Knowledge (PMBOK® Guide), Sixth ed. Newtown Square, Pennsylvania, USA. https://www.pmi.org/pmbok-guide-standards

Ramasamy, S., Antony, J. & Kumar, M. (2021). Lean Six Sigma for sustainability: Current status and future directions. Journal of Cleaner Production, 278, 123840. https://doi.org/10.1016/j.jclepro.2020.123840

Rani, H. A. & Arlianti, N. (2024). Dasar-dasar Statistika dan Probabilitas dalam Ilmu Sains. Yogyakarta, Indonesia: Deepublish. https://books.google.co.id/books/about/Dasar_Dasar_Statistika_Dan_Probabilitas.html?id=GO8uEQAAQBAJ&redir_esc=y

Riaz, H., Khan, K. I. A., Ullah, F., Tahir, M. B., Alqurashi, M. & Alsulami, B. T.  (2023a). Key factors for implementation of total quality management in construction sector: A system dynamics approach. Ain Shams Engineering Journal, 14(3). https://www.sciencedirect.com/science/article/pii/S2090447922002143

Riaz, H., Khan, K. I. A. & Alqurashi, M. (2023b). Framework for enhancing quality assurance in construction management. Ain Shams Engineering Journal, 14(3), 101786. https://doi.org/10.1016/j.asej.2023.101786

Sunder, M. V. & Antony, J. (2020). A strategic framework for Lean Six Sigma project management: Insights from stakeholder management perspective. The TQM Journal, 32(6), 1239–1260. https://doi.org/10.1108/TQM-07-2019-0188

Timans, W., Antony, J. & Kumar, V. (2021). Lean Six Sigma in small and medium-sized manufacturing enterprises: The Dutch experience. International Journal of Production Research, 59(3), 901–917. https://doi.org/10.1080/00207543.2020.1715873

Uluskan, M., Joines, J. A. & Antony, J. (2021). Quality management in global supply chains: A systematic review. Supply Chain Management: An International Journal, 26(4), 321–342. https://doi.org/10.1108/SCM-05-2020-0209

Wahyu, A., Suryani, F. & Dinariana, D. (2021). Kemampuan pengelolaan manajemen mutu terhadap hasil kerja diukur dari standar QPASS (Studi kasus: Proyek Arandra Residence). IKRAITH-Teknologi, 5(2), 48–57. https://journals.upi-yai.ac.id/index.php/ikraith-teknologi/article/view/969

Yadav, G., Seth, D. & Desai, T. N. (2021). Application of hybrid Lean Six Sigma framework in manufacturing: An empirical study. Production Planning & Control, 32(8), 618–632. https://doi.org/10.1080/09537287.2020.1828756

Zhang, M., Wang, W. & Antony, J. (2022). Comprehensive Lean Six Sigma applications in complex systems: A review. Production Planning & Control, 33(10), 901–920. https://doi.org/10.1080/09537287.2021.1957889

Zuhri, Z., Isya, M. & Rani, H. A. (2018). Pengaruh faktor-faktor kualifikasi kontraktor terhadap kualitas proyek konstruksi jalan di Kota Banda Aceh. Jurnal Arsip Rekayasa Sipil dan Perencanaan, 1(3), 113–121. https://jurnal.usk.ac.id/JARSP/article/view/11775